## Toate taskurile
ID | Epic | Faza | Zi/Ord | Task | Detalii + Definition of Done | Owner | Ore | Depinde de | Branch | Status
T001 | E0 Setup | MVP | Z1 | Repo GitHub privat + .gitignore | Repo creat, .gitignore Python (venv, .env, __pycache__, .pytest_cache). DoD: clone curat functioneaza. | S | 0.5 | - | chore/T001-repo-init | todo
T002 | E0 Setup | MVP | Z1 | Branch protection pe main | Require PR + required status checks + delete branch on merge. DoD: push direct pe main respins. | S | 0.5 | T001 | - | todo
T003 | E0 Setup | MVP | Z1 | PR template + CODEOWNERS | Template cu: ce face / cum s-a testat / ID task. CODEOWNERS: prompts/ si docs/*.sql cer review. DoD: PR nou vine precompletat. | J | 0.5 | T001 | chore/T003-pr-template | todo
T004 | E0 Setup | MVP | Z1 | CI: ruff (lint+format) | GitHub Actions pe PR: ruff check + ruff format --check. DoD: cod neformatat pica CI. | S | 1 | T001 | chore/T004-ci-ruff | todo
T005 | E0 Setup | MVP | Z1 | CI: pytest | Job pytest cu cache pip, Python 3.12. DoD: test picat blocheaza merge. | S | 1 | T004 | chore/T005-ci-pytest | todo
T006 | E0 Setup | MVP | Z1 | requirements.txt pin-uit | fastapi, uvicorn, asyncpg, redis, openai, pydantic v2, pydantic-settings, httpx, pytest, pytest-asyncio, fakeredis, ruff. Versiuni fixe. DoD: pip install -r curat pe Python 3.12. | J | 1 | T001 | chore/T006-requirements | todo
T007 | E0 Setup | MVP | Z1 | .env.example complet | Toate variabilele: Supabase, OpenAI, Meta (token, verify_token, phone_number_id, app_secret), Redis, plafoane. DoD: nicio valoare reala in el. | J | 0.5 | T006 | chore/T007-env-example | todo
T008 | E0 Setup | MVP | Z1 | Schelet foldere src/ | Structura exacta din CLAUDE.md (webhook/, worker/stages/, tools/, agent/, db/queries/, jobs/, gdpr/, proactive/) cu __init__.py. DoD: import src.* merge. | J | 1 | T006 | chore/T008-skeleton | todo
T009 | E0 Setup | MVP | Z1 | docker-compose dev | Redis + webhook (uvicorn reload) + worker; Postgres = Supabase remote. DoD: docker compose up porneste tot, healthcheck verde. | J | 2 | T008 | chore/T009-compose-dev | todo
T010 | E0 Setup | MVP | Z1 | Dockerfile multi-stage | Build slim, non-root user, layer caching pe requirements. DoD: imagine < 300MB, porneste webhook si worker. | S | 1.5 | T006 | chore/T010-dockerfile | todo
T011 | E0 Setup | P1 | O2 | Makefile / scripts dev | make run / test / lint / compose-up. DoD: juniorul porneste tot cu o comanda. | J | 0.5 | T009 | chore/T011-makefile | todo
T012 | E0 Setup | MVP | Z1 | CLAUDE.md + CONTRIBUTING.md in repo | Versiunile finale comise in root. DoD: Claude Code le citeste la start de sesiune. | J | 0.5 | T001 | docs/T012-claude-md | todo
T013 | E0 Setup | MVP | Z1 | Meta developer app + WhatsApp test number | App creat, numar sandbox, token generat, numerele voastre adaugate ca destinatari de test. DoD: poti trimite hello world din Graph API Explorer pe telefonul tau. CRITIC ZIUA 1. | S | 1.5 | - | - | todo
T014 | E0 Setup | MVP | Z1 | Webhook verify endpoint (GET) | hub.mode/hub.challenge/hub.verify_token. DoD: Meta accepta URL-ul de webhook. | S | 0.5 | T013 | feat/T014-webhook-verify | todo
T015 | E0 Setup | MVP | Z1 | Tunel local dev (cloudflared) | Tunel stabil catre localhost:8000 pt webhook in dev. DoD: mesaj de pe telefon ajunge in FastAPI local. | S | 1 | T014 | - | todo
T016 | E0 Setup | MVP | Z1 | Start verificare Meta Business | Documente depuse pt numarul de productie. Proces 3-15 zile, paralel, nu blocheaza. DoD: cerere depusa, status urmarit in plan. | S | 1 | T013 | - | todo
T017 | E0 Setup | MVP | Z1 | OpenAI: chei + limite spend | Chei separate dev/prod, hard limit lunar, soft alert. DoD: limita vizibila in dashboard OpenAI. | S | 0.5 | - | - | todo
T018 | E0 Setup | MVP | Z1 | Supabase: chei + PITR check | Service key doar pe server, anon key nefolosit de bot, PITR activ verificat. DoD: backup point-in-time confirmat in dashboard. | S | 0.5 | - | - | todo
T020 | E1 DB | MVP | Z1 | Review 001_schema vs CLAUDE.md | Diff intre schema existenta si CLAUDE.md actualizat; lista exacta pt 002. DoD: lista verificata de amandoi. | S | 1 | T012 | - | todo
T021 | E1 DB | MVP | Z1-2 | 002: conv.outbox | idempotency_key UNIQUE, status, attempts, next_attempt_at, index pe due. DoD: insert duplicat pe idempotency_key respins. | S | 1 | T020 | feat/T021-sql-outbox | todo
T022 | E1 DB | MVP | Z1-2 | 002: conv.channel_identities | Tabel + migrare datelor existente din contacts (channel/external_user_id) + UNIQUE. DoD: fiecare contact demo are exact o identitate. | S | 1.5 | T020 | feat/T022-sql-identities | todo
T023 | E1 DB | MVP | Z1-2 | 002: checkout_links + attribution pe orders | ref_code UNIQUE, cart jsonb + orders.attributed_checkout_link_id, attribution. DoD: FK-uri valide. | S | 1 | T020 | feat/T023-sql-attribution | todo
T024 | E1 DB | MVP | Z1-2 | 002: catalog.product_embeddings | vector(1536), content_hash, HNSW cosine. DoD: index folosit in EXPLAIN pe query test. | S | 1 | T020 | feat/T024-sql-embeddings | todo
T025 | E1 DB | MVP | Z1-2 | 002: language pe faq/cache/templates | Coloana language + default ro + backfill + in chei de lookup. DoD: query fara language pe astea = code review fail. | S | 0.5 | T020 | feat/T025-sql-language | todo
T026 | E1 DB | MVP | Z1-2 | 002: contacts last_inbound_at/consent/erased_at | 3 coloane + backfill last_inbound_at din MAX(messages.created_at). DoD: backfill corect pe demo. | S | 0.5 | T020 | feat/T026-sql-contacts | todo
T027 | E1 DB | MVP | Z1-2 | 002: messages provider_message_id + status | Coloane + index pe (business_id, provider_message_id). DoD: lookup status O(1). | S | 0.5 | T020 | feat/T027-sql-msg-status | todo
T028 | E1 DB | MVP | Z1-2 | 002: core.wa_templates | Lifecycle draft->approved, language, category, version. DoD: CHECK-uri pe status/category. | S | 0.5 | T020 | feat/T028-sql-templates | todo
T029 | E1 DB | MVP | Z1-2 | 002: analytics.usage_daily | PK (business_id, day), toate contoarele + revenue_attributed. DoD: upsert idempotent testat. | S | 0.5 | T020 | feat/T029-sql-usage | todo
T030 | E1 DB | MVP | Z1-2 | 002: gdpr_requests + audit_log + gdpr_erase_contact() | Functia anonimizeaza contact+identities+messages+orders.phone si scrie audit. DoD: rulata pe contact test, telefonul dispare peste tot. | S | 1.5 | T020 | feat/T030-sql-gdpr | todo
T031 | E1 DB | MVP | Z1-2 | 002: back_in_stock_subscriptions | Tabel + UNIQUE(business,contact,product,variant). DoD: dublu-subscribe nu duplica. | S | 0.5 | T020 | feat/T031-sql-bis | todo
T032 | E1 DB | MVP | Z1-2 | 002: indexuri lipsa | messages(conversation_id,created_at), outbox due partial, faq_aliases(normalized,language), response_cache HNSW. DoD: EXPLAIN pe query-urile hot foloseste indexul. | S | 1 | T021 | feat/T032-sql-indexes | todo
T033 | E1 DB | MVP | Z2 | 002: RLS defense-in-depth | RLS pe conv.* si catalog.* cu current_setting(app.business_id); rolurile fara bypassrls pe ele. DoD: query fara GUC setat = 0 randuri. | S | 1.5 | T021 | feat/T033-sql-rls | todo
T034 | E1 DB | MVP | Z2 | Rulare 002 pe Supabase + verificare | Toate migrarile in ordine pe staging-ul DB; datele din 010 intacte (count-uri identice). DoD: raport count inainte/dupa. | S | 1 | T021-T033 | - | todo
T035 | E1 DB | MVP | Z2 | Seed: 10 comenzi test in conv.orders | Statusuri variate + tracking_url + telefoane test. DoD: check_order are pe ce lucra. | J | 1 | T034 | feat/T035-seed-orders | todo
T036 | E1 DB | MVP | Z2 | Seed: clarification_templates RO | Min 5 missing_fields (buget, categorie, nuanta, tip ten, ocazie). DoD: template per camp, text natural RO. | J | 1 | T034 | feat/T036-seed-clarify | todo
T037 | E1 DB | MVP | Z2 | Spot-check 20 produse demo | Pret/stoc/link/ai_summary corecte; raport in issue + fix-uri. DoD: raport scris, anomaliile corectate. | J | 2 | T034 | - | todo
T038 | E1 DB | P1 | O1 | Script backup/restore local | pg_dump schema+date pt dev local si restore documentat. DoD: restore testat o data. | J | 2 | T034 | chore/T038-backup-script | todo
T040 | E2 Fundatie | MVP | Z2 | config.py (BaseSettings) | Toate env-urile tipizate, fail-fast cu mesaj clar la lipsa. DoD: test lipsa OPENAI_API_KEY -> crash explicit la boot. | J | 2 | T007 | feat/T040-config | todo
T041 | E2 Fundatie | MVP | Z2 | models: TurnContext | Dataclass cu toate campurile + docstring cine-l scrie (regula un-singur-scriitor). DoD: mypy curat. | S | 1.5 | T008 | feat/T041-turncontext | todo
T042 | E2 Fundatie | MVP | Z2 | models: contracte Pydantic | RouteDecision, Reply, ToolResult, InboundMessage, Event — validari stricte. DoD: JSON invalid de la LLM ridica ValidationError, nu crash. | S | 2 | T041 | feat/T042-contracts | todo
T043 | E2 Fundatie | MVP | Z2 | models: ConversationState | Schema state + serializare + verificare 8KB inainte de save (mirror al CHECK din DB). DoD: state >8KB respins in cod cu eroare clara. | S | 1.5 | T041 | feat/T043-state | todo
T044 | E2 Fundatie | MVP | Z2 | db/connection.py | Pool asyncpg, context manager, SET app.business_id per checkout din pool, healthcheck. DoD: test ca GUC e setat pe fiecare conexiune. | S | 2.5 | T034,T040 | feat/T044-db-pool | todo
T045 | E2 Fundatie | MVP | Z2-3 | db/queries/conv.py | get_or_create_contact (via channel_identities), load/save state, insert message, load history(8). DoD: teste integrare pe business demo. | S | 3 | T044 | feat/T045-queries-conv | todo
T046 | E2 Fundatie | MVP | Z3 | db/queries/catalog.py | load taxonomy, faq+aliases, clarification templates, produse pe id-uri. DoD: toate cu business_id+language unde e cazul. | S | 2 | T044 | feat/T046-queries-catalog | todo
T047 | E2 Fundatie | MVP | Z3 | db/queries/analytics.py | insert message_event, insert llm_call, insert debug_snapshot. DoD: doar INSERT-uri (append-only respectat). | J | 1.5 | T044 | feat/T047-queries-analytics | todo
T048 | E2 Fundatie | MVP | Z2 | Redis client + ping | Client async, settings din config, healthcheck. DoD: compose up -> ping ok. | J | 1 | T040 | feat/T048-redis-client | todo
T049 | E2 Fundatie | MVP | Z3 | Redis: producer + consumer group | XADD inbound:{conversation_id} + XREADGROUP cu ack + claim pe mesaje moarte. DoD: mesaj neack-uit e reluat de alt consumer. | S | 2.5 | T048 | feat/T049-redis-streams | todo
T050 | E2 Fundatie | MVP | Z3 | Redis: lock per conversatie | SET NX cu TTL + extend + release safe (token). DoD: 2 workeri pe aceeasi conversatie -> unul asteapta. | S | 1.5 | T049 | feat/T050-redis-lock | todo
T051 | E2 Fundatie | MVP | Z3 | Redis: debounce adaptiv 2-3s | Acumulare mesaje rapide intr-un lot; trigger la liniste. DoD: 3 mesaje in 2s devin UN lot cu 3 intrari, nu string lipit. | S | 2 | T049 | feat/T051-debounce | todo
T052 | E2 Fundatie | P1 | O2 | Redis: rate limit per user | Token bucket per (business, contact). DoD: 30 msg/min -> throttle, contorizat in events. | S | 1 | T048 | feat/T052-rate-limit | todo
T053 | E2 Fundatie | MVP | Z2 | Logging JSON + trace_id | structlog/logging JSON, trace_id per tur propagat. DoD: un tur e filtrabil cap-coada dupa trace_id. | J | 1.5 | T040 | feat/T053-logging | todo
T054 | E2 Fundatie | MVP | Z2 | PII redaction in logger | Filter care mascheaza telefoane (+40724***) oriunde apar. DoD: test ca un numar nu trece de logger. | J | 1.5 | T053 | feat/T054-pii-redaction | todo
T055 | E2 Fundatie | MVP | Z3 | pytest conftest + fixtures | Fake TurnContext factory, fakeredis, business demo id, mesaje factory. DoD: folosite de min 2 teste. | J | 2 | T042 | test/T055-fixtures | todo
T056 | E2 Fundatie | MVP | Z3 | Handler global de erori FastAPI | Erori custom + raspuns 200 la Meta chiar si pe eroare interna (altfel retry storm) + log. DoD: exceptie in handler -> Meta primeste 200, eroarea e logata. | S | 1 | T053 | feat/T056-error-handler | todo
T060 | E3 Webhook | MVP | Z3 | FastAPI app + /health | App factory, /health verifica DB+Redis. DoD: compose up -> /health 200. | J | 1 | T040 | feat/T060-app-health | todo
T061 | E3 Webhook | MVP | Z3-4 | Semnatura X-Hub-Signature-256 | HMAC cu app_secret, comparatie constant-time. DoD: semnatura gresita -> 403; test cu payload real. | S | 1.5 | T060 | feat/T061-signature | todo
T062 | E3 Webhook | MVP | Z4 | Parser payload Meta -> InboundMessage | Text, interactive (buton/lista), media (doar tip+id in MVP), contacts, context(reply-to). DoD: 6 payload-uri reale din docs Meta parsate corect. | S | 2.5 | T042 | feat/T062-payload-parser | todo
T063 | E3 Webhook | MVP | Z4 | Dedupe pe provider_message_id | [AUDIT] ABSORBIT IN NX-51 (dedupe 2 straturi): Redis SETNX EX 48h in webhook + tabel public.inbound_dedupe NE-partitionat (schema_v2 pierduse tabelul; unique-ul pe messages partitionat nu opreste retry-urile Meta). Vezi cardul NX-51. | S | 0 | T045 | feat/T063-dedupe | -> NX-51
T064 | E3 Webhook | MVP | Z4 | Update last_inbound_at + XADD + ACK<50ms | Fire-and-forget pe scrieri grele; ACK imediat. DoD: p95 ACK < 50ms masurat in test. | S | 1.5 | T049,T063 | feat/T064-ack-fast | todo
T065 | E3 Webhook | P1 | O1 | Status receiver delivered/read/failed | Update conv.messages.status pe provider_message_id + event analytics + failed -> log warn. DoD: payload-uri reale de status procesate. | J | 3 | T062 | feat/T065-status-receiver | todo
T066 | E3 Webhook | MVP | Z5 | Test e2e webhook | Sandbox -> tunel -> parser -> dedupe -> stream; cu telefon real. DoD: mesaj de pe telefon vizibil in Redis stream cu trace_id. | S | 1 | T061-T064 | test/T066-webhook-e2e | todo
T070 | E4 Pipeline | MVP | Z4 | Runner: executie stagii + early exit | Lista ordonata de stagii, ctx.reply -> sare la sender, exceptie -> degradare. DoD: stagiile sunt functii pure primite ca lista (testabil). | S | 2.5 | T041 | feat/T070-runner-core | todo
T071 | E4 Pipeline | MVP | Z4 | Runner: masurare + message_event | Latency per stagiu, tokens/cost agregat din ctx.events, scriere message_event la final. DoD: stagiile nu stiu ca sunt masurate. | S | 2 | T070,T047 | feat/T071-runner-metrics | todo
T072 | E4 Pipeline | MVP | Z4 | Consumer -> runner | Lotul debounced devine un tur; lock tinut pe durata turului. DoD: doua loturi pe aceeasi conversatie ruleaza serializat. | S | 1.5 | T051,T070 | feat/T072-consumer-runner | todo
T073 | E4 Pipeline | MVP | Z4-5 | Gates: bot_active + handoff_until | bot_active false -> early exit notificare; handoff_until in viitor -> tacere totala. DoD: teste pe ambele cai. | S | 1 | T070 | feat/T073-gates-handoff | todo
T074 | E4 Pipeline | P1 | O2 | Gates: risc patterns | Lista regex (amenintari, legal, medical, furie extrema) -> request_human. DoD: 10 fraze risc detectate, 10 normale trecute. | S | 1.5 | T073 | feat/T074-gates-risk | todo
T075 | E4 Pipeline | P1 | O2 | Gates: language detect RO/HU/EN | Heuristic + fallback (lingua / py3langid), sticky pe conversatie in state. DoD: 30 fraze test, accuratete >90%. | S | 1.5 | T073 | feat/T075-gates-language | todo
T076 | E4 Pipeline | MVP | Z5 | Gates: media ack politicos (MVP) | Vocale/poze -> raspuns politicos ca momentan textul e canalul + event media_received. DoD: nu crapa pe niciun tip media. | J | 1 | T073 | feat/T076-gates-media | todo
T077 | E4 Pipeline | MVP | Z6 | f_normalize (diacritice, spatii, lowercase) | Functie pura folosita identic la scriere si la lookup aliase. DoD: "Cât costă livrarea?!" == "cat costa livrarea". | J | 1 | T055 | feat/T077-normalize | todo
T078 | E4 Pipeline | MVP | Z6 | Free layer: FAQ alias lookup | normalized -> faq_aliases (business+language) -> answer -> reply + event cache_type=faq. DoD: hit = zero LLM, <100ms. | S | 2 | T077,T046 | feat/T078-faq-alias | todo
T079 | E4 Pipeline | MVP | Z6 | Free layer: clarify pe pending_question | State are pending_question -> template din clarification_templates -> reply. DoD: flux narrow (lipseste buget) testat. | S | 1.5 | T078 | feat/T079-clarify | todo
T080 | E4 Pipeline | P1 | O1 | Cache semantic: lookup | Embedding query -> cosine response_cache (business+language, prag 0.92, expires_at). DoD: hit/miss logat cu scor. | S | 2.5 | T046 | feat/T080-semcache-read | todo
T081 | E4 Pipeline | P1 | O1 | Cache semantic: write-through | Dupa validator, raspunsurile cache-abile (faq-like, fara preturi volatile) se scriu cu TTL. DoD: aceeasi intrebare a 2-a oara = hit. | S | 1.5 | T080 | feat/T081-semcache-write | todo
T082 | E4 Pipeline | MVP | Z7 | Triaj: prompt nano + JSON validat | ~300 tokens input, output RouteDecision prin Pydantic, retry 1 la JSON invalid. DoD: 20 fraze etichetate, >=18 corecte. | S | 2.5 | T042 | feat/T082-triage-core | todo
T083 | E4 Pipeline | MVP | Z7 | Triaj: validare category_key vs taxonomy | Key inexistent -> CLARIFY (nu trece mai departe). DoD: categorie inventata de nano e prinsa. | S | 1 | T082,T046 | feat/T083-triage-taxonomy | todo
T084 | E4 Pipeline | MVP | Z7 | Triaj: simple -> raspuns pe nano | Salut/multumesc/program -> nano compune direct, early exit. DoD: "multumesc" nu ajunge la mini. | S | 1 | T082 | feat/T084-triage-simple | todo
T085 | E4 Pipeline | MVP | Z7 | Context builder: istoric + profil | Max 8 mesaje + profil compact din contacts.profile + state. DoD: bugetul respectat indiferent de lungimea conversatiei. | S | 2 | T045 | feat/T085-ctx-core | todo
T086 | E4 Pipeline | MVP | Z7 | Context builder: prefix byte-identic | System+tools identic intre tururi pt prompt caching OpenAI. DoD: test hash(prefix) identic pe 2 tururi; cached_tokens >0 in usage. | S | 1.5 | T085 | feat/T086-ctx-caching | todo
T087 | E4 Pipeline | P1 | O2 | Context builder: summarizer >20 mesaje | Rezumat nano + ultimele 8; rezumatul in conv.short_memory. DoD: conversatie de 30 mesaje incape in buget. | S | 2.5 | T085 | feat/T087-ctx-summarizer | todo
T088 | E4 Pipeline | MVP | Z8 | Agent: loop tool calls (max 3 in cod) | Mini cu tools, executie din registry, al 4-lea call refuzat de runner. DoD: limita e in cod, nu in prompt. | S | 3.5 | T042,T100 | feat/T088-agent-loop | todo
T089 | E4 Pipeline | MVP | Z8 | Agent: buying stages + state update | browsing/narrowing/comparing/ready_to_buy in prompt + tranzitii scrise in state. DoD: stage-ul evolueaza logic pe o conversatie golden. | S | 2 | T088 | feat/T089-agent-stages | todo
T090 | E4 Pipeline | MVP | Z8 | Agent: trunchiere tool results | Max 6 produse x 8 campuri impus la granita tool->prompt. DoD: tool care intoarce 50 produse -> agentul vede 6. | S | 1 | T088 | feat/T090-agent-truncate | todo
T091 | E4 Pipeline | MVP | Z9 | Validator: extractie pret/produs/link | Regex+parser pe reply: cifre cu lei/RON, nume produse, URL-uri. DoD: extractia corecta pe 10 reply-uri reale. | S | 2 | T088 | feat/T091-validator-extract | todo
T092 | E4 Pipeline | MVP | Z9 | Validator: verificare vs retrieval + 1 retry | Orice pret/produs/link inexistent in ctx.retrieval -> retry cu feedback explicit. DoD: pret inventat injectat -> blocat. | S | 1.5 | T091 | feat/T092-validator-check | todo
T093 | E4 Pipeline | MVP | Z9 | Validator: fallback fara cifre | Al 2-lea esec -> reformulare fara cifre/linkuri + event validator_failed. DoD: clientul primeste raspuns util, fara date inventate. | S | 1 | T092 | feat/T093-validator-fallback | todo
T094 | E4 Pipeline | MVP | Z9-10 | Lant degradare (niciodata tacere) | mini timeout->retry->nano->template "revin imediat"+alerta. DoD: OpenAI mock down -> clientul tot primeste mesaj in <10s. | S | 2.5 | T088 | feat/T094-degradation | todo
T095 | E4 Pipeline | MVP | Z5 | Sender: typing indicator | Trimis instant la intrarea in pipeline (fire-and-forget). DoD: typing vizibil pe telefon inainte de raspuns. | S | 1 | T064 | feat/T095-typing | todo
T096 | E4 Pipeline | MVP | Z5 | Sender: split natural >200 chars | Spargere pe propozitii/paragrafe, max 2 mesaje. DoD: nu taie in mijlocul cuvantului/linkului. | J | 1.5 | T070 | feat/T096-split | todo
T097 | E4 Pipeline | MVP | Z5 | Sender: TX unica outbox+state+event | O singura tranzactie DB: insert outbox + update state + insert message. DoD: crash intre pasi imposibil (atomic). | S | 2.5 | T045,T021 | feat/T097-sender-tx | todo
T098 | E4 Pipeline | MVP | Z5 | Dispatcher: outbox -> Meta + wamid | Poll due, send, salveaza provider_message_id pe conv.messages, marcheaza sent. DoD: kill mid-send -> restart nu dubleaza (idempotency_key). | S | 2.5 | T097 | feat/T098-dispatcher | todo
T099 | E4 Pipeline | MVP | Z5 | Dispatcher: retry backoff + dead | Exponential 1s->2m, max 5, apoi dead + alerta. DoD: Meta mock 500 -> retry-uri corecte, apoi dead. | S | 1.5 | T098 | feat/T099-dispatcher-retry | todo
T100 | E4 Pipeline | MVP | Z6 | Tools: base + registry per business | ToolResult, registry citit din business.settings (tool-uri activate). DoD: tool dezactivat cerut -> eroare controlata. | J | 2.5 | T042 | feat/T100-tools-base | todo
T101 | E4 Pipeline | MVP | Z6 | OpenAI adapter (LLM client) | Wrapper async: model, timeout, usage capture (tokens/cached/cost), erori tipizate. DoD: orice apel LLM trece prin adapter, usage in ctx.events. | S | 2.5 | T040 | feat/T101-llm-adapter | todo
T102 | E4 Pipeline | P1 | O3 | Post-tur: extractor profil (nano) | Async dupa send: atribute noi (tip ten, preferinte) -> contacts.profile merge. DoD: nu blocheaza turul; profil imbogatit vizibil. | S | 2.5 | T098 | feat/T102-profile-extractor | todo
T103 | E4 Pipeline | P1 | O3 | Post-tur: lead score update | Reguli pe semnale (buying stage, checkout link, frecventa) -> contacts. DoD: scor creste pe conversatia golden de vanzare. | J | 2 | T102 | feat/T103-lead-score | todo
T104 | E4 Pipeline | P1 | O3 | Post-tur: alias candidates | Intrebari care au ratat FAQ dar au primit raspuns bun -> faq_alias_candidates pending. DoD: candidatul apare pt aprobare. | J | 2 | T102 | feat/T104-alias-candidates | todo
T110 | E5 Tools | MVP | Z6 | Job: embed_products (content_hash) | ai_summary -> text-embedding-3-small -> product_embeddings; idempotent. DoD: 221 produse populate; re-rulare = 0 apeluri. | S | 2 | T024 | feat/T110-embed-job | todo
T111 | E5 Tools | MVP | Z8 | search_products: filtre SQL | category/concerns/suitable_for/budget din taxonomy mapate pe WHERE. DoD: filtrele exclud corect (budget_max strict). | S | 2.5 | T046 | feat/T111-search-sql | todo
T112 | E5 Tools | MVP | Z8 | search_products: ranking pgvector | Pe subsetul filtrat: ORDER BY embedding <=> query_embedding. DoD: "ceva pentru ten uscat iarna" da rezultate relevante. | S | 2 | T111,T110 | feat/T112-search-vector | todo
T113 | E5 Tools | MVP | Z8 | search_products: shape rezultat | Max 6 x 8 campuri (id,name,brand,min_price,url,ai_summary scurt,stock,shade). DoD: niciodata obiect complet catre agent. | S | 1 | T112 | feat/T113-search-shape | todo
T114 | E5 Tools | MVP | Z8-9 | search_products: 10 query-uri reale validate | Lista S+J de query-uri beauty reale; relevanta verificata manual. DoD: 8/10 relevante; fix-uri la prag/ranking daca nu. | S | 1.5 | T113 | test/T114-search-eval | todo
T115 | E5 Tools | MVP | Z9 | get_product_details | Detalii + variante + review summary cu fallback elegant daca lipseste. DoD: testat pe 5 produse demo. | J | 2.5 | T100 | feat/T115-product-details | todo
T116 | E5 Tools | MVP | Z9 | faq_lookup (tool agent) | Cautare faq+knowledge_guides filtrat language (pt cand agentul are nevoie explicit). DoD: hit si miss testate. | J | 2 | T100 | feat/T116-faq-tool | todo
T117 | E5 Tools | MVP | Z9-10 | check_order | Lookup numar comanda SAU telefon -> status+tracking. DoD: ambele cai pe cele 10 comenzi seed. | J | 2.5 | T100,T035 | feat/T117-check-order | todo
T118 | E5 Tools | MVP | Z10 | request_human + notificare operator | handoff_until set + mesaj catre operator (Slack webhook sau WhatsApp). DoD: dupa handoff botul tace pana expira. | S | 2 | T100 | feat/T118-request-human | todo
T119 | E5 Tools | MVP | Z11 | cart_add + checkout_link | Cos in state (ref-uri!) + insert conv.checkout_links cu ref_code + URL cu ?ref=. DoD: linkul contine ref si cosul corect. | S | 2.5 | T100,T023 | feat/T119-checkout | todo
T120 | E5 Tools | MVP | Z8 | tool_definitions: scheme OpenAI | Generate din registry; test automat schema==semnatura functiei. DoD: drift schema/functie pica CI. | J | 2.5 | T100 | feat/T120-tool-schemas | todo
T121 | E5 Tools | P1 | O2 | compare_products | Diferente structurate 2-3 produse (pret, atribute cheie, pros/cons din reviews). DoD: tabel comparativ corect pe produse demo. | J | 3 | T115 | feat/T121-compare | todo
T122 | E5 Tools | P1 | O3 | subscribe_back_in_stock | Insert subscriptions + confirmare. DoD: dublu-subscribe idempotent. | J | 1.5 | T031 | feat/T122-bis-tool | todo
T123 | E5 Tools | P1 | O4 | reorder | Ultimele comenzi ale contactului -> sugestie reorder. DoD: contact cu istoric primeste sugestia corecta. | J | 2 | T117 | feat/T123-reorder | todo
T124 | E5 Tools | P1 | O4 | delivery_eta | ETA din date curier/ERP (stub configurabil per business pana la integrare reala). DoD: raspuns rezonabil per oras. | J | 2 | T100 | feat/T124-eta | todo
T125 | E5 Tools | P1 | O5 | book_appointment + Google Calendar | conv.bookings + event in calendar + confirmare. DoD: programare vizibila in calendar test. (Pt verticala salon/auto.) | S | 4 | T100 | feat/T125-booking | todo
T130 | E6 Prompts | MVP | Z7 | prompt_builder din taxonomy | System prompt generat per business din catalog.taxonomy; zero hardcodari. DoD: taxonomie noua in DB -> in prompt fara cod. | S | 2.5 | T046 | feat/T130-prompt-builder | todo
T131 | E6 Prompts | MVP | Z7 | Persona + reguli de vanzare (beauty) | Ton RO natural, mutari de vanzare per buying stage, interdictii (nu inventa, nu promite). DoD: review comun pe 5 conversatii. | S | 2 | T130 | feat/T131-persona | todo
T132 | E6 Prompts | P1 | O2 | Prompt versioning | Hash-ul promptului in message_events; prompturile in repo (prompts/). DoD: stii exact ce prompt a generat orice raspuns. | J | 1.5 | T130 | feat/T132-prompt-version | todo
T133 | E6 Prompts | P2 | O8 | Few-shots per vertical | Exemple bune per verticala in prompt builder. DoD: calitate masurata inainte/dupa pe golden. | S | 3 | T130 | feat/T133-fewshots | todo
T140 | E7 Teste | MVP | Z9 | LLM replay/mock pt teste | Inregistrare raspunsuri LLM pe fixtures + replay determinist in CI (zero apeluri reale). DoD: golden ruleaza offline. | S | 2.5 | T101 | test/T140-llm-replay | todo
T141 | E7 Teste | MVP | Z9-10 | Golden: beauty_search.json | Conversatie completa cautare->detalii->recomandare; assert pe route, tools, validator. DoD: ruleaza in CI <20s. | J | 2 | T140 | test/T141-golden-search | todo
T142 | E7 Teste | MVP | Z10 | Golden: faq_hit.json | Intrebare FAQ -> hit pe alias, zero LLM. DoD: assert cache_type=faq, llm_calls=0. | J | 1 | T140 | test/T142-golden-faq | todo
T143 | E7 Teste | MVP | Z10 | Golden: order_status.json | "unde e comanda 1234" -> check_order -> raspuns cu tracking. DoD: assert tool corect + status corect. | J | 1 | T140 | test/T143-golden-order | todo
T144 | E7 Teste | P1 | O1 | Golden: clarify + handoff | Mesaj ambiguu -> clarify; mesaj risc -> handoff + tacere. DoD: ambele fluxuri verzi. | J | 1.5 | T140 | test/T144-golden-edge | todo
T145 | E7 Teste | MVP | Z10 | Test tenant isolation | Toate query-urile refuza date cu alt business_id (GUC gresit -> 0 randuri). DoD: ruleaza pe toate functiile din db/queries. | S | 2 | T033 | test/T145-tenant-isolation | todo
T146 | E7 Teste | MVP | Z10 | Test idempotenta outbox + dedupe | Webhook duplicat si dispatcher restartat -> exact un mesaj trimis. DoD: chaos test verde. | S | 1.5 | T098 | test/T146-idempotency | todo
T147 | E7 Teste | P1 | O1 | Load test 50 conversatii | Script async 50 conversatii concurente pe staging; p95, erori, mesaje pierdute. DoD: p95<6s cu LLM, zero pierderi. | S | 3 | M2 | test/T147-load | todo
T148 | E7 Teste | P1 | O2 | Coverage gate in CI | pytest-cov, prag 70% pe src/, exclus boilerplate. DoD: sub prag pica CI. | J | 1 | T005 | test/T148-coverage | todo
T149 | E7 Teste | P1 | O1 | Chaos: kill worker mid-turn | Omoara workerul in mijlocul turului -> lock expira, mesajul e reluat, clientul primeste raspuns o data. DoD: verificat manual pe staging. | S | 1.5 | T146 | test/T149-chaos | todo
T155 | E8 Deploy | MVP | Z11 | VPS hardening | User non-root, ssh key-only, ufw (80/443/ssh), fail2ban, unattended-upgrades. DoD: scan porturi curat. | S | 2 | - | chore/T155-vps-hardening | todo
T156 | E8 Deploy | MVP | Z11 | Compose prod + staging separate | Doua proiecte compose (staging/prod), env separat, resurse limitate. DoD: ambele ruleaza izolat pe acelasi VPS. | S | 2 | T155,T010 | chore/T156-compose-prod | todo
T157 | E8 Deploy | MVP | Z11 | Caddy TLS + domenii | staging.domeniu.ro + api.domeniu.ro, certuri auto. DoD: webhook public HTTPS stabil, Meta pointat pe staging. | S | 1.5 | T156 | chore/T157-caddy-tls | todo
T158 | E8 Deploy | MVP | Z11 | Secrets pe server | Fisiere env per mediu, permisiuni 600, in afara repo-ului. DoD: niciun secret in git history (verificat cu gitleaks). | S | 1 | T156 | chore/T158-secrets | todo
T159 | E8 Deploy | MVP | Z12 | CD: auto-deploy staging | Merge in main -> build imagine -> deploy staging (Actions + ssh sau watchtower). DoD: merge ajunge pe staging <5 min. | S | 2 | T156,T005 | chore/T159-cd-staging | todo
T160 | E8 Deploy | MVP | Z12 | CD: prod cu approve manual | Environment protection in GitHub, approve -> deploy prod. DoD: prod nu se schimba fara click explicit. | S | 1 | T159 | chore/T160-cd-prod | todo
T161 | E8 Deploy | P1 | O1 | Rollback documentat + testat | Tag imagini per release, rollback = redeploy tag anterior. DoD: rollback executat o data pe staging, <5 min. | S | 1 | T159 | chore/T161-rollback | todo
T162 | E8 Deploy | P1 | O1 | Restore test din PITR | Restore Supabase intr-un proiect temporar, verificare date. DoD: RTO/RPO masurate si scrise in runbook. | S | 2 | T018 | chore/T162-restore-test | todo
T165 | E9 Observ | MVP | Z12 | Sentry (sau GlitchTip) integrat | Erori webhook+worker cu trace_id si business_id (fara PII). DoD: eroare fortata apare cu context complet. | J | 1.5 | T053 | feat/T165-sentry | todo
T166 | E9 Observ | MVP | Z12 | Cost & latenta: query-uri standard | SQL-uri salvate: cost/zi per business, p95 latenta, cache hit rate, route mix. DoD: rulabile in Supabase Studio, documentate. | J | 1.5 | T047 | feat/T166-cost-queries | todo
T167 | E9 Observ | P1 | O1 | Alerting minim | Alerta pe: erori repetate, cost spike (>2x media), dispatcher dead letters. Canal: Slack/email. DoD: fiecare alerta testata fortat. | J | 2 | T165 | feat/T167-alerting | todo
T168 | E9 Observ | MVP | Z13 | Sonda sintetica e2e la 5 min | Cron: mesaj test -> verifica raspuns <30s -> alerta la 2 esecuri. DoD: oprirea workerului declanseaza alerta. | J | 2 | T157 | feat/T168-probe | todo
T169 | E9 Observ | P1 | O2 | Uptime monitor + status intern | Uptime-kuma (sau extern) pe /health staging+prod. DoD: downtime vizibil cu istoric. | J | 1 | T157 | chore/T169-uptime | todo
T170 | E9 Observ | P1 | O3 | Dashboard Metabase pe analytics | Metabase pe Supabase read-only: cost, conversii, cache hit, handoffs per business. DoD: 5 grafice utilizabile in discutia cu clientul. | J | 3 | T166 | feat/T170-metabase | todo
T175 | E10 GDPR | P1 | O2 | Abuse blocklist | contacts.is_blocked (sau settings) -> gates early exit silentios + audit. DoD: numar blocat nu consuma LLM. | S | 1 | T073 | feat/T175-blocklist | todo
T176 | E10 GDPR | P1 | O1 | Cost guard zilnic per business | Contor Redis cost/zi, la plafon -> handoff politicos + alerta + event. DoD: test cu plafon 0.01 USD. | S | 1.5 | T101 | feat/T176-cost-guard | todo
T177 | E10 GDPR | P1 | O1 | gdpr_erase e2e + endpoint admin | Endpoint protejat care ruleaza functia + verificare ca PII a disparut peste tot. DoD: test automat pe contact sintetic. OBLIGATORIU inainte de clienti reali. | S | 2.5 | T030 | feat/T177-gdpr-erase | todo
T178 | E10 GDPR | P1 | O1 | Export date contact (GDPR access) | JSON cu mesaje+profil+comenzi per contact, livrat ca fisier. DoD: export complet pe contact test. | J | 2 | T177 | feat/T178-gdpr-export | todo
T179 | E10 GDPR | P1 | O2 | Retentie: job anonimizare 12 luni | Cron lunar: messages.content=NULL la >12 luni (configurabil per business). DoD: dry-run cu raport inainte de delete real. | J | 2 | T177 | feat/T179-retention | todo
T180 | E10 GDPR | MVP | Z11-12 | Nota informare in primul mesaj | [AUDIT: LAUNCH-BLOCKING - AI Act art. 50, aplicabil 2 aug 2026, amenzi 15 mil EUR/3%] La primul contact: o linie despre asistent AI + link politica. Extins de NX-10 (per limba, per canal, proactiv). DoD: apare exact o data per contact; golden test verifica. | J | 1 | T045 | feat/T180-privacy-note | todo
T181 | E10 GDPR | P1 | O2 | DPA template + politica retentie | Document DPA pt clienti + politica scrisa. DoD: review-uit (ideal de un avocat) inainte de clientul 1. | S | 2 | - | docs/T181-dpa | todo
T182 | E10 GDPR | P1 | O3 | Cleanup job: dedupe 48h + snapshots + short_memory | Cron care curata inbound_dedupe>48h, debug_snapshots>14z, short_memory>7z. DoD: tabelele nu cresc nelimitat. | J | 1.5 | T034 | feat/T182-cleanup | todo
T183 | E10 GDPR | P2 | O7 | Replay protection webhook | Timestamp check pe payload (>5 min vechi -> drop) + nonce. DoD: replay-ul unui payload vechi e respins. | S | 1.5 | T061 | feat/T183-replay-protect | todo
T188 | E11 Comert | MVP | Z11-12 | Webhook orders (stub generic) | Endpoint generic POST /orders care primeste comenzi (format propriu) -> conv.orders. DoD: comanda simulata intra corect. [AUDIT] Din prima zi cu HMAC per business + idempotenta (business_id, external_id) - vezi NX-52; nu ramane stub liber in productie. | J | 2 | T023 | feat/T188-orders-webhook | todo
T189 | E11 Comert | MVP | Z12 | Match ref_code -> attribution | Comanda cu ?ref= -> checkout_links -> orders.attribution=direct_bot + converted_order_id. DoD: comanda simulata cu ref apare atribuita. | J | 1.5 | T188,T119 | feat/T189-attribution | todo
T190 | E11 Comert | P1 | O2 | Revenue atribuit in usage_daily | Rollup-ul aduna orders atribuite pe zi. DoD: cifra din dashboard = suma comenzilor atribuite. | J | 1 | T189 | feat/T190-revenue-rollup | todo
T191 | E11 Comert | P1 | O4 | Click tracking pe checkout links | Redirect scurt /r/{ref} -> clicked_at -> URL final. DoD: click inregistrat inainte de redirect. | J | 2 | T119 | feat/T191-click-tracking | todo
T195 | E12 Analytics | P1 | O1 | Job rollup usage_daily | Nocturn: message_events+llm_calls+orders -> usage_daily upsert. DoD: re-rulare pe aceeasi zi = aceleasi cifre (idempotent). | J | 2.5 | T029 | feat/T195-rollup | todo
T196 | E12 Analytics | P1 | O3 | Raport lunar per client | Script: PDF/HTML cu conversatii, conversii, revenue atribuit, cost — pt factura retainer. DoD: raport generat pe demo. | J | 3 | T195 | feat/T196-monthly-report | todo
T197 | E12 Analytics | P2 | O6 | Intents breakdown in usage_daily | Agregare intent->count pe zi din events. DoD: top 10 intents vizibile per saptamana. | J | 1.5 | T195 | feat/T197-intents | todo
T200 | E13 Proactiv | P1 | O2 | Scheduler skeleton (cron async) | Proces separat, joburi din DB, retry, idempotenta per job. DoD: job test ruleaza la timp, exact o data. | S | 2.5 | T098 | feat/T200-scheduler | todo
T201 | E13 Proactiv | P1 | O2 | Guard: consent + 24h window | Functie unica: are opt-in? in fereastra? -> mesaj normal / template approved / skip logat. DoD: toate cele 3 cai testate. | S | 2 | T200 | feat/T201-proactive-guard | todo
T202 | E13 Proactiv | P1 | O3 | wa_templates: CRUD + submit la Meta | Creare/versionare in DB + submit prin API + sync status aprobare. DoD: un template utility aprobat end-to-end. | S | 3 | T028 | feat/T202-templates | todo
T203 | E13 Proactiv | P1 | O3 | Flux AWB updates | Eveniment curier (stub/webhook) -> mesaj status comanda prin guard. DoD: update AWB simulat ajunge pe WhatsApp corect. | S | 2.5 | T201 | feat/T203-awb | todo
T204 | E13 Proactiv | P1 | O4 | Back-in-stock notify | La sync stoc>0 -> notifica subscriptions neexpirate + marcheaza notified_at. DoD: o singura notificare per subscriptie. | J | 2 | T201,T122 | feat/T204-bis-notify | todo
T205 | E13 Proactiv | P1 | O4 | Follow-up cos abandonat | State cu cart + inactivitate 24h -> follow-up prin guard (template daca e in afara ferestrei). DoD: simulare completa pe demo. | S | 2.5 | T201,T119 | feat/T205-abandoned-cart | todo
T206 | E13 Proactiv | P1 | O3 | Opt-out handling (STOP) | "stop/dezabonare" -> consent revocat + confirmare + audit. DoD: dupa STOP, zero mesaje proactive. | J | 1.5 | T201 | feat/T206-optout | todo
T210 | E14 Sync | P1 | O1 | Discovery platforma client 1 | Aflat la vanzare: platforma (Shopify/Woo/feed), acces API/feed, frecventa. DoD: decizie scrisa de connector. BLOCHEAZA restul epicului. | S | 1 | - | - | todo
T211 | E14 Sync | P1 | O2 | Connector feed/API (per platforma) | Fetch + parse + mapare pe catalog.products/variants. DoD: catalogul clientului 1 importat complet pe staging. | S | 6 | T210 | feat/T211-sync-connector | todo
T212 | E14 Sync | P1 | O2 | Upsert idempotent + diff | external_id ca cheie, doar randurile schimbate, soft-delete pe disparute. DoD: sync de 2 ori = zero modificari a 2-a oara. | S | 2.5 | T211 | feat/T212-sync-upsert | todo
T213 | E14 Sync | P1 | O3 | Quality alerts (alerta, nu publicare) | Anomalii: pret 0/10x, stoc inghetat, linkuri moarte -> alerta, produsul NU intra activ. DoD: anomalie injectata e prinsa. | S | 2 | T212 | feat/T213-quality-alerts | todo
T214 | E14 Sync | P1 | O3 | Re-embed la schimbari | Sync-ul atinge ai_summary -> embed job doar pe content_hash schimbat + invalidare semantic cache afectat. DoD: pret schimbat NU re-embeduieste; descriere schimbata DA. | S | 1.5 | T212,T110 | feat/T214-sync-reembed | todo
T215 | E14 Sync | P2 | O6 | Review summaries job | Reviews per produs -> sumar+pros/cons (nano, batch) -> review_summaries. DoD: 20 produse cu sumar coerent. | S | 3 | T212 | feat/T215-review-intel | todo
T216 | E14 Sync | P1 | O3 | Taxonomie + FAQ clientul 1 | Workshop cu clientul: categorii, concerns, aliase, 15+ FAQ-uri. DoD: taxonomy+faq populate si validate de client. | S | 4 | T210 | feat/T216-client1-taxonomy | todo
T220 | E15 Dashboard | P2 | O5 | Spec dashboard (pe baza Metabase) | Ce intrebari pune clientul lunar -> spec UI minimal. DoD: spec validat cu 1-2 clienti reali. | S | 2 | T170 | docs/T220-dashboard-spec | todo
T221 | E15 Dashboard | P2 | O6 | Inbox handoff (UI minimal) | Lista conversatii in handoff + istoric + raspunde ca om + retur catre bot. DoD: operatorul preia si returneaza o conversatie. | S | 8 | T220 | feat/T221-inbox | todo
T222 | E15 Dashboard | P2 | O6 | Aprobare aliase + FAQ din UI | Lista candidates pending -> approve/reject -> devin aliase live. DoD: flux complet din UI. | J | 4 | T221 | feat/T222-alias-approval | todo
T223 | E15 Dashboard | P2 | O7 | Analytics + revenue per client (UI) | Graficele din Metabase aduse in dashboardul propriu. DoD: clientul isi vede singur cifrele. | S | 8 | T221 | feat/T223-analytics-ui | todo
T224 | E15 Dashboard | P2 | O7 | Toggle bot_active + setari business | On/off per conversatie si global, working hours, plafoane. DoD: schimbarile au efect imediat in gates. | J | 3 | T221 | feat/T224-settings-ui | todo
T228 | E16 Eval | P2 | O5 | LLM-as-judge nocturn (2-3% sample) | Scoruri: utilitate, acuratete, ton, vanzare -> conversation_evals. DoD: raport saptamanal cu trend. | S | 4 | T140 | feat/T228-llm-judge | todo
T229 | E16 Eval | P2 | O6 | Eval gate in CI | Schimbare de prompt -> golden + eval pe set fix; sub prag -> blocat. DoD: prompt degradat intentionat e prins. | S | 3 | T228 | feat/T229-eval-gate | todo
T230 | E16 Eval | P2 | O7 | Canary 5% + promovare pe cifre | Prompt nou la 5% din conversatii, comparatie metrici, promovare/rollback. DoD: un ciclu complet rulat. | S | 4 | T229 | feat/T230-canary | todo
T231 | E16 Eval | P1 | O4 | Golden tests din corectii shadow | Corectiile operatorului devin fixtures noi automat. DoD: o corectie reala a generat un golden. | J | 2 | T144 | feat/T231-golden-from-shadow | todo
T235 | E17 Limbi | P1 | O4 | FAQ + clarify templates HU | Traduse + intrari cu language=hu. DoD: conversatie test in HU primeste raspunsuri HU. | J | 3 | T036 | feat/T235-hu | todo
T236 | E17 Limbi | P1 | O5 | FAQ + clarify templates EN | Idem EN. DoD: conversatie EN completa. | J | 2 | T235 | feat/T236-en | todo
T237 | E17 Limbi | P1 | O5 | Golden per limba | beauty_search in HU si EN. DoD: verzi in CI. | J | 1.5 | T235 | test/T237-golden-langs | todo
T240 | E18 Media | P2 | O6 | STT vocale (Whisper) | Download media Meta -> Whisper -> textul intra in pipeline normal. DoD: vocala in RO transcrisa si procesata. | S | 3 | T076 | feat/T240-stt | todo
T241 | E18 Media | P2 | O7 | Vision: poza -> match catalog | Poza produs -> embedding/descriere -> cautare in catalog. DoD: poza unui produs demo gaseste produsul corect in top 3. | S | 5 | T240 | feat/T241-vision | todo
T242 | E18 Media | P2 | O7 | Media storage cu TTL | Media descarcata in object storage cu expirare 30z, doar ref in DB. DoD: fisierele expira automat. | J | 2 | T240 | feat/T242-media-storage | todo
T245 | E19 Canale | P2 | O8 | Adapter Telegram | Webhook+send Telegram in spatele aceleiasi interfete de canal. DoD: pipeline-ul nu stie pe ce canal e. | S | 5 | T062 | feat/T245-telegram | todo
T246 | E19 Canale | P2 | O8 | Identity resolution e2e | Acelasi telefon pe WA+TG -> un contact, profil unificat. DoD: test cu ambele identitati. | S | 2 | T245,T022 | feat/T246-identity-e2e | todo
T250 | E20 Client1 | P1 | O1 | Chestionar onboarding client | Platforma, FAQ-uri, tonul brandului, plafoane, program, escaladare. DoD: document completat de client. | S | 1.5 | - | docs/T250-onboarding-form | todo
T251 | E20 Client1 | P1 | O2 | Numar WhatsApp productie + display name | Dupa verificare Meta (T016): numar dedicat client, display name aprobat. DoD: numar live pe contul clientului. | S | 2 | T016 | - | todo
T252 | E20 Client1 | P1 | O3 | Template-uri client submise + aprobate | Min: order_update, back_in_stock, follow_up in RO. DoD: toate approved in Meta. | S | 2 | T202,T251 | - | todo
T253 | E20 Client1 | P1 | O3 | Shadow mode 1 saptamana | Botul propune, omul aproba (sau monitorizare pasiva); corectiile devin aliase+golden. DoD: rata de corectie <10% inainte de go-live. | S | 4 | T216 | feat/T253-shadow-mode | todo
T254 | E20 Client1 | P1 | O4 | Executie go-live checklist | Checklist-ul din diagrama Deployment, bifat item cu item cu clientul. DoD: semnat de ambele parti. | S | 2 | T253 | - | todo
T255 | E20 Client1 | P1 | O4 | Training operator client | 30 min: inbox handoff, aprobare FAQ, cand intervine. DoD: operatorul executa un handoff singur. | J | 2 | T254 | - | todo
NX-50 | E29 Corectit. | MVP | Z2 | P0-A: conexiune worker pe rol bot_runtime | Pool asyncpg pe conexiunea directa 5432 (sau session-mode) cu rol LOGIN bot_runtime + set_config(app.business_id) per checkout; SAU SET LOCAL per tranzactie. Eliminat login postgres din worker. DoD: niciun drum de cod nu ruleaza ca postgres; current_user=bot_runtime in toate query-urile. | S | 6 | T044 | feat/NX-50-db-role | todo
NX-51 | E29 Corectit. | MVP | Z2 | P0-B: dedupe inbound in 2 straturi | Redis SET NX EX 172800 pe dedupe:{business_id}:{wamid} in webhook + tabel public.inbound_dedupe NE-partitionat (PK business_id+provider_msg_id) + cleanup 48h. Inlocuieste T063. DoD: acelasi payload de 3x -> exact 1 intrare in stream si 1 mesaj in DB. | S | 5 | T048 | feat/NX-51-dedupe | todo
NX-52 | E29 Corectit. | MVP | Z11-12 | P0: HMAC + idempotenta pe /orders | Secret per business (businesses.orders_webhook_secret), header X-Nativx-Signature (sha256) verificat constant-time, idempotenta pe (business_id, external_id), 401 + audit_log la semnatura invalida. DoD: payload nesemnat respins; aceeasi comanda de 2x = 1 rand in orders. | S | 4 | T188 | feat/NX-52-orders-hmac | todo
NX-53 | E29 Corectit. | MVP | Z3 | Test de izolare CONCURENT | 50 tururi paralele pe 2 tenanti: assert zero cross-contamination pe current_user / GUC / rezultate; ruleaza in CI marcat slow. DoD: 0 esecuri pe 20 de rulari consecutive. | S | 4 | NX-50 | test/NX-53-isolation | todo
NX-04 | E21 Edge | MVP | Z2 | Assert rol DB la checkout din pool | La fiecare checkout: assert current_user=bot_runtime si app.business_id non-null; raise IsolationError altfel (fail-fast, nu query gresit). DoD: test cu rol gresit -> exceptie inainte de orice query. | S | 2 | NX-50 | feat/NX-04-pool-assert | todo
NX-02 | E21 Edge | MVP | Z2 | Redis durabil + securizat | requirepass + bind privat + appendonly yes (everysec) + maxmemory-policy noeviction in compose. DoD: restart Redis nu pierde mesaje din stream; conexiunea fara parola e respinsa. | S | 2 | T048 | chore/NX-02-redis-aof | todo
NX-40 | E28 Date | MVP | Z3 | pg_partman: partitii automate | pg_partman + pg_cron pe messages si analytics_events, premake 2 luni, alerta daca lipseste partitia urmatoare. DoD: partitia lunii viitoare exista automat; insert in luna noua nu crapa. | S | 3 | T020 | feat/NX-40-partman | todo
NX-10 | E22 AI Act | MVP | Z11 | Disclosure AI complet (extinde T180) | Text per limba RO/HU/EN, trigger exact o data per contact per canal, varianta pentru template-uri proactive, doc de conformitate art. 50. DoD: golden test verifica prezenta in primul mesaj. | J | 4 | T180 | feat/NX-10-disclosure | todo
NX-01 | E21 Edge | MVP | Z13 | Cloudflare in fata webhook-ului | DNS proxied, SSL Full (strict), WAF managed rules, rate limit pe /webhook, ufw allow doar IP-urile Cloudflare. DoD: accesul direct pe IP-ul VPS e respins; webhook-ul functioneaza prin CF. | S | 3 | T157 | - | todo
NX-03 | E21 Edge | MVP | Z13 | Alerte: consumer lag + outbox depth | Job la 60s: XINFO GROUPS (lag), outbox pending count + max age -> analytics_events + alerta Slack la praguri. DoD: alerta declansata in test la lag simulat. | S | 4 | T167 | feat/NX-03-lag-alerts | todo
NX-11 | E21 Edge | P1 | O1 | systemd units + healthchecks | webhook / worker / dispatcher / scheduler ca unitati separate cu restart=always + healthcheck per serviciu. DoD: kill -9 pe worker -> repornit <10s, restul neafectate. | S | 3 | T156 | chore/NX-11-systemd | todo
NX-14 | E22 AI Act | P1 | O1 | Supabase regiune UE + decizie OpenAI EU | Verifica/migreaza proiectul Supabase in UE; decizie scrisa privind EU data residency la OpenAI (cost ~+10% pe nano). DoD: regiunea confirmata in dashboard + decizia in docs/. | S | 4 | T018 | - | todo
NX-13 | E22 AI Act | P1 | O2 | Registru procesatori + nota informare | OpenAI / Supabase / Meta / Cloudflare in registrul de procesatori + actualizare politica + link in disclosure. DoD: document publicat, link functional din primul mesaj. | J | 3 | T181 | docs/NX-13-procesatori | todo
NX-41 | E28 Date | P1 | O1 | create_tenant.py idempotent | Script onboarding: business, channel, channel_identity, rol, plafoane, FAQ seed - rerulabil fara duplicate. DoD: 2 rulari consecutive = stare identica in DB. | S | 6 | T044 | feat/NX-41-create-tenant | todo
NX-43 | E28 Date | P1 | O2 | Schema contacts.profile (whitelist) | Whitelist de chei per vertical din taxonomie + enforcement in extractor (cheile necunoscute -> drop + event). DoD: o cheie din afara whitelist-ului nu intra in profil. | S | 4 | T130 | feat/NX-43-profile-schema | todo
NX-42 | E28 Date | P1 | O3 | pip-audit + renovate + digest pin | pip-audit in CI (fail pe high), config renovate, imaginile de prod pin-uite pe digest. DoD: CI pica pe un CVE high cunoscut. | J | 4 | T005 | chore/NX-42-supply-chain | todo
NX-12 | E25 LLM | P1 | O1 | Failover LLM OpenAI -> Anthropic | Provider 2 in adapter: interfata comuna, traducere tool schemas, circuit breaker (N esecuri -> cooldown), flag per business. DoD: cu OpenAI blocat in test, conversatia continua pe providerul 2. | S | 16 | T101 | feat/NX-12-llm-failover | todo
NX-15 | E25 LLM | P1 | O1 | Moderation gate inbound | Endpoint de moderation (gratuit) inainte de triaj; flagged -> raspuns neutru + event, fara apel la agent. DoD: mesaj flagged nu ajunge la agent. | J | 3 | T101 | feat/NX-15-moderation | todo
NX-16 | E25 LLM | P1 | O1 | Golden: injectie + jailbreak | 5 fixture de prompt-injection + 3 de jailbreak social; assert: fara system prompt leak, fara date de alt tenant, fara discount inventat. Gate in CI. DoD: CI rosu daca o aparare cade. | S | 4 | T140 | test/NX-16-golden-injection | todo
NX-17 | E25 LLM | P1 | O2 | schema_version in payload stream | Camp schema_version in payload-urile inbound/outbound + toleranta N-1 in consumer. DoD: deploy cu versiune noua proceseaza mesajele vechi din coada. | J | 3 | T049 | feat/NX-17-schema-version | todo
NX-05 | E23 WA Ops | P1 | O1 | Quality rating monitor + pauza proactiv | Webhook/polling pe quality_rating + messaging tier per numar -> analytics + alerta; la LOW, pauza automata pe proactiv. DoD: simulare LOW -> proactiv oprit + alerta trimisa. | S | 6 | T065 | feat/NX-05-quality-monitor | todo
NX-07 | E23 WA Ops | P1 | O2 | Pacing proactiv + quiet hours | Cap mesaje proactive / contact / saptamana + quiet hours pe businesses.timezone + spread pe ore. DoD: job-ul nu trimite noaptea si respecta cap-ul. | S | 6 | T201 | feat/NX-07-pacing | todo
NX-08 | E24 Handoff | P1 | O1 | Inbox-lite handoff pe Slack | Thread per conversatie in handoff: ultimele 8 mesaje; comenzi reply (-> outbox) si return-to-bot. DoD: operatorul raspunde din Slack si clientul primeste pe WhatsApp. | S | 12 | T118 | feat/NX-08-slack-inbox | todo
NX-54 | E29 Corectit. | P1 | O2 | Tarife Meta per piata in config | Rate card per tara in config (nu hardcodat) + recalcul cost template RO/HU pe noile tarife in vigoare de la 1 iul 2026 + linie de cost canal in raportul lunar. DoD: schimbarea tarifului = doar editare de config. | S | 4 | T196 | feat/NX-54-rate-cards | todo
NX-33 | E27 Selling | P1 | O3 | Funnel + cohorte in Metabase | Funnel intent -> reco -> checkout -> order + cohorta de revenire; definitia "assisted revenue" scrisa. DoD: dashboard cu cele 2 vizualizari pe demo. | J | 8 | T195 | - | todo
NX-30 | E27 Selling | P2 | - | Promotions: tabel + tool + validator | Tabel promotions per business + tool read-only get_promotions + regula in validator: orice discount mentionat apartine promotions active. DoD: discount inventat -> blocat de validator. | S | 20 | T094 | feat/NX-30-promotions | todo
NX-32 | E27 Selling | P2 | - | Cross-sell map + free-shipping gap | Mapare complementara per categorie din taxonomie + semnal "X lei pana la transport gratuit" in context builder. DoD: recomandarea complementara apare in golden testul de upsell. | S | 16 | T130 | feat/NX-32-cross-sell | todo
NX-31 | E27 Selling | P2 | - | Export CRM: webhook + CSV zilnic | Webhook lead.qualified (HMAC, acelasi mecanism ca NX-52) + CSV zilnic per tenant in storage. DoD: lead calificat ajunge in endpoint-ul de test + fisierul zilnic exista. | J | 12 | T120 | feat/NX-31-crm-export | todo
NX-06 | E23 WA Ops | P2 | - | CTWA referral -> atribuire ads | Parse referral (ad_id, source) -> analytics_events + raport per campanie; fereastra de 72h marcata in window tracker. DoD: mesaj CTWA simulat apare in raport cu ad_id. | J | 6 | T062 | feat/NX-06-ctwa | todo
NX-09 | E23 WA Ops | P2 | - | Retry failed re-engagement | Mesaj proactiv failed dupa 24h -> template approved, max 1 retry. DoD: failed simulat -> exact un retry pe template. | J | 4 | T099 | feat/NX-09-retry | todo
NX-20 | E26 Widget | P2 | W1 | Widget gateway SSE | POST /web/messages + GET /web/stream (SSE), sesiune semnata (token public per tenant), rate limit IP/visitor, reconectare Last-Event-ID. DoD: 200 de sesiuni simultane stabile pe staging. | S | 20 | T157 | feat/NX-20-sse-gateway | todo
NX-21 | E26 Widget | P2 | W2 | widget.js embeddabil | Shadow DOM, embed 1 linie, tema din settings tenant, i18n RO/HU/EN, disclosure AI vizibil (art. 50). DoD: functioneaza pe un site tert de test fara conflicte CSS. | S | 24 | NX-20 | feat/NX-21-widget-js | todo
NX-22 | E26 Widget | P2 | W3 | Canal web in gates/sender | channel_kind=web: fara fereastra 24h, debounce scurt, typing = eveniment SSE, sender scrie in stream-ul SSE. DoD: golden echo pe canalul web trece. | S | 12 | NX-20 | feat/NX-22-web-channel | todo
NX-25 | E26 Widget | P2 | W3 | CORS/CSP + allowlist embed | Allowlist de domenii per tenant + token public + CSP recomandat in docul de instalare. DoD: embed de pe un domeniu neautorizat e respins. | S | 8 | NX-20 | feat/NX-25-cors | todo
NX-23 | E26 Widget | P2 | W4 | Identitate vizitator + merge auditat | visitor_id semnat in cookie -> channel_identities; capturarea telefonului -> merge cu identitatea WhatsApp, logat in audit. DoD: merge-ul leaga istoricul fara duplicate. | S | 16 | NX-22 | feat/NX-23-identity-merge | todo
NX-24 | E26 Widget | P2 | W5 | Context pagina in payload | page_url / product_id trimise de widget -> hint de retrieval in context builder. DoD: o intrebare pusa pe pagina unui produs raspunde despre ACEL produs. | J | 8 | NX-22 | feat/NX-24-page-context | todo
NX-26 | E26 Widget | P2 | W6 | Golden web + load SSE | Suite golden pe canalul web + load test 200 sesiuni / 10 min. DoD: p95 sub tinta, 0 mesaje pierdute. | S | 12 | NX-22 | test/NX-26-web-golden | todo
|  |  |  | Ore MVP Senior |  |  | 157.5
|  |  |  | Ore MVP Junior |  |  | 53
|  |  |  | Ore P1 total |  |  | 214.5
|  |  |  | Ore P2 total |  |  | 220
|  |  |  | Numar taskuri |  |  | 230
Capacitate 2 sapt (13 zile lucrate): S=10h/zi=130h din care ~8h review PR junior => ~122h pe taskuri. J=4h/zi=52h => ~4h tampon. Cifrele de mai sus trebuie sa fie sub aceste praguri.

## Legenda + Milestones
Element | Explicatie
Faza MVP | Intra in cele 2 saptamani. Zi = ziua planificata (Z1-Z14). Albastru=Senior, Verde=Junior.
Faza P1 (mov) | Saptamanile 3-5: tot ce trebuie inainte/imediat dupa clientul 1 real. Ordinea O1-O5 = prioritate.
Faza P2 (gri) | Dupa primul client stabil: dashboard propriu, eval pipeline, media, multi-canal.
M1 — Echo e2e (Ziua 5) | Mesaj de pe telefon -> raspuns automat prin tot pipeline-ul (gates->sender->dispatcher), outbox idempotent, trace_id cap-coada. Taskuri: T001-T099 (fara cele de inteligenta).
M2 — Conversatie de vanzare (Ziua 10) | Pe demo beauty: cautare -> detalii -> recomandare validata structural; FAQ/cache hit cand se poate; golden tests verzi. Taskuri cheie: T078-T094, T110-T120, T130-T131, T140-T146.
M3 — Prod live, demo-ready (Ziua 14) | Staging verde, deploy prod TLS, sonda activa, atribuire simulata mergand, runbook scris. Taskuri: T147-T189 (MVP).
Regula de taiere | Daca MVP-ul derapeaza, se muta in P1 (in ordine): T114 (eval search), T096 (split natural), T188-T189 (atribuire simulata). NU se taie niciodata: validator, outbox, dedupe, golden tests.
MVP = limba RO | Language detect (T075) si cache-ul semantic (T080-T081) s-au mutat in P1 ca sa incapa MVP-ul in 2 saptamani. In MVP limba e ro hardcodat in gates, free layer = doar FAQ aliases. Structura de limba din DB ramane pregatita.
P1-O1 = primele dupa MVP | T177 (gdpr_erase), T195 (rollup), T210 (discovery platforma!), T250 (chestionar client), T162 (restore test).
Blocaj extern 1 | T016 verificarea Meta Business: 3-15 zile, porneste ziua 1. Demo merge pe sandbox; go-live real (T251) depinde de ea.
Blocaj extern 2 | T210 platforma magazinului clientului 1: intreaba la PRIMA discutie comerciala. Tot epicul E14 e blocat fara raspuns.
Audit CTO 12.06.2026 | Randurile NX-xx (epicele E21-E29) = backlogul nou din audit. P0 INAINTEA webhook-ului (G2): NX-50, NX-51, NX-02, NX-04; NX-53 imediat dupa. T063 absorbit in NX-51; T180 mutat in MVP (AI Act art. 50, 2 aug 2026); T188 primeste HMAC din prima zi (NX-52).
Epice noi (audit) | E21 Edge/rezilienta - E22 AI Act/GDPR - E23 WhatsApp ops - E24 Handoff - E25 LLM robustete - E26 Web Widget (V1.5) - E27 Vanzare avansata - E28 Date/calitate - E29 Corectitudine multi-tenant.
Carduri detaliate NX | nativx_carduri_NX_audit.zip: 13 carduri complete (format T0xx) pentru taskurile imediate + NX_backlog_compact.md pentru restul. Analiza completa: Nativx_Audit_CTO_iunie_2026.md.
Ord W1-W6 / estimari NX | W1-W6 = ordinea interna a epicului E26 Widget (dupa clientul 1 pe WhatsApp). Estimarile NX sunt in ore (1 zi = 8h).

## Reguli Git + Claude Code
# | Regula | Detaliu
1 | main e protejat | Zero push direct. Orice schimbare = branch + PR + CI verde. GitHub: Settings -> Branches -> rule pe main.
2 | Branch per task | feat/T112-search-vector — ID-ul taskului in nume. Max 2-3 zile de viata; mai mult = taskul era prea mare.
3 | PR-uri mici | Un PR = un task (sau 2-3 taskuri SQL mici inrudite). Sub ~400 linii diff cand se poate.
4 | Review asimetric | PR junior: review senior obligatoriu. PR senior: CI verde + self-merge. Exceptie: prompts/ si docs/*.sql — celalalt se uita mereu (CODEOWNERS forteaza).
5 | Teste obligatorii | DoD-ul fiecarui task include test. Golden tests la ORICE schimbare de prompt/agent.
6 | Commits conventionale | feat: / fix: / test: / chore: / docs:
7 | Claude Code per task | O sesiune = un task = un branch. Da-i ID-ul + DoD-ul din acest fisier; CLAUDE.md e contextul permanent. Inainte de push: ruff + pytest local.
8 | Standup 10 min zilnic | Ce am terminat / ce incep / ce ma blocheaza. Junior blocat >30 min -> intreaba.
9 | Secrete | Niciodata in repo. .env gitignored; pe VPS fisiere env 600 in afara repo. Gitleaks in CI (bonus).
10 | Definition of Done global | Cod + test trece + CI verde + merge + branch sters. Fara test nu e gata, e doar scris.

## Audit NX detalii
ID | Epic | Titlu | Prio | Faza | Impact business | Complexitate | Ore | Depinde de | De ce / risc acoperit
NX-50 | E29 | P0-A: conexiune worker pe rol bot_runtime | P0 | MVP Z2 | Previne query pe tenantul gresit / bypass RLS | M | 6 | T044 | Izolarea multi-tenant nu are voie sa depinda de starea de sesiune a unui pooler transaction-mode (S5). Reparat acum = ore; dupa M2 = re-testarea intregului flux.
NX-51 | E29 | P0-B: dedupe inbound in 2 straturi | P0 | MVP Z2 | Elimina raspunsurile duble catre clientul final + cost LLM dublu | S | 5 | T048 | Unique-ul (business_id, provider_msg_id, created_at) pe messages partitionat nu opreste retry-urile Meta (S14). Se face inainte de POST /webhook.
NX-52 | E29 | HMAC + idempotenta pe /orders | P0 | MVP Z11-12 | Protejeaza cifra de revenue atribuit = baza retainerului | S | 4 | T188 | Fara autentificare per tenant, comenzi false pot umfla/polua atribuirea (S15).
NX-53 | E29 | Test de izolare concurent (50 tururi, 2 tenanti) | P0 | MVP Z3 | Dovada ca izolarea tine sub load real | S | 4 | NX-50 | Testul existent (T145) a trecut doar secvential - exact scenariul concurent e cel riscant.
NX-04 | E21 | Assert rol DB la checkout din pool | P0 | MVP Z2 | Fail-fast in loc de date gresite | XS | 2 | NX-50 | Strat de siguranta peste NX-50: orice regresie viitoare pica zgomotos, nu tacut.
NX-02 | E21 | Redis durabil + securizat (AOF everysec) | P0 | MVP Z2 | Zero mesaje de client pierdute la restart | XS | 2 | T048 | Azi un restart Redis pierde mesajele primite si neprocesate (S4).
NX-40 | E28 | pg_partman: partitii automate | P0 | MVP Z3 | Evita oprirea insert-urilor in luna 3 | XS | 3 | T020 | Partitiile messages/analytics_events sunt create manual; fara automatizare, prima luna fara partitie = incident.
NX-10 | E22 | Disclosure AI complet (extinde T180) | P0 | MVP Z11 | Conformitate AI Act art. 50 (2 aug 2026) | S | 4 | T180 | Amenzi pana la 15 mil EUR / 3% cifra de afaceri; niciun client live fara disclosure.
NX-01 | E21 | Cloudflare in fata webhook-ului | P0 | MVP Z13 | Elimina clasa de atacuri direct-pe-IP | XS | 3 | T157 | Versiunea pragmatica (2-3h) a casutei "WAF + API Gateway" din diagrama (S3).
NX-03 | E21 | Alerte consumer lag + outbox depth | P0 | MVP Z13 | Afli tu primul ca pipeline-ul sufoca, nu clientul | S | 4 | T167 | Semnal timpuriu de saturatie; completeaza sonda e2e.
NX-11 | E21 | systemd units + healthchecks separate | P1 | P1 O1 | "A cazut agentul" nu mai inseamna "a cazut tot" | XS | 3 | T156 | Procese separate cu restart policy - efort aproape zero, structura src/ o permite deja.
NX-14 | E22 | Supabase regiune UE + decizie OpenAI EU | P1 | P1 O1 | Baza pentru DPA-uri si clienti enterprise | S | 4 | T018 | Rezidenta datelor in UE inainte de primul contact real in DB (S10).
NX-13 | E22 | Registru procesatori + nota informare | P1 | P1 O2 | Transparenta GDPR ceruta la orice audit de client | XS | 3 | T181 | OpenAI/Supabase/Meta/Cloudflare documentati o singura data, refolosit la fiecare client.
NX-41 | E28 | create_tenant.py idempotent | P1 | P1 O1 | Onboarding client nou in minute, fara pasi manuali uitati | S | 6 | T044 | Devine API-ul control plane-ului la faza C (celule).
NX-43 | E28 | Schema whitelist pt. contacts.profile | P1 | P1 O2 | Profilul ramane curat si utilizabil in prompt | S | 4 | T130 | Fara whitelist, extractorul LLM umple profilul cu chei arbitrare -> buget de context risipit.
NX-42 | E28 | pip-audit + renovate + digest pin | P1 | P1 O3 | Supply chain: CVE-urile nu intra nevazute | XS | 4 | T005 | Cerinta standard la orice due-diligence de client mare.
NX-12 | E25 | Failover LLM OpenAI -> Anthropic | P1 | P1 O1 | Un outage OpenAI nu mai inseamna "botul tace" | L | 16 | T101 | Incalcarea principiului 6 la nivel de platforma; ca biblioteca in adapter, nu microserviciu.
NX-15 | E25 | Moderation gate inbound | P1 | P1 O1 | Continut abuziv nu ajunge la agent | XS | 3 | T101 | Endpoint gratuit; reduce si risc legal si cost.
NX-16 | E25 | Golden tests injectie + jailbreak | P1 | P1 O1 | Apararile de siguranta nu regreseaza nevazut | S | 4 | T140 | 5 fixture injection + 3 jailbreak, gate in CI (S2/S13).
NX-17 | E25 | schema_version in payload stream | P1 | P1 O2 | Deploy fara drenarea cozii | XS | 3 | T049 | Toleranta N-1 = zero mesaje blocate la release.
NX-05 | E23 | Quality rating monitor + pauza proactiv | P1 | P1 O1 | Un ban Meta = produsul mort; il vezi inainte | S | 6 | T065 | Rating LOW -> pauza automata pe proactiv + alerta.
NX-07 | E23 | Pacing proactiv + quiet hours | P1 | P1 O2 | Reputatia numarului + experienta clientului final | S | 6 | T201 | Cap/contact/saptamana + timezone per business.
NX-08 | E24 | Inbox-lite handoff pe Slack | P1 | P1 O1 | Handoff-ul devine functional fara dashboard-ul din P2 | M | 12 | T118 | Fara raspunsul operatorului, handoff-ul e o fundatura; shadow mode (T253) depinde de el.
NX-54 | E29 | Tarife Meta per piata in config | P1 | P1 O2 | Costul per conversatie ramane corect dupa 1 iul 2026 | S | 4 | T196 | RO si HU ies din "Rest of" pe rate card propriu - exact pietele tinta.
NX-33 | E27 | Funnel + cohorte in Metabase | P1 | P1 O3 | Clientul isi vede ROI-ul -> apara retainerul | S | 8 | T195 | Definitia "assisted revenue" scrisa o singura data, citata in contracte.
NX-30 | E27 | Promotions: tabel + tool + regula validator | P1 | P2 | Prima cerinta a oricarui magazin in sezon de reduceri | L | 20 | T094 | Validatorul garanteaza: niciun discount inventat de model.
NX-32 | E27 | Cross-sell map + free-shipping gap | P1 | P2 | Upsell determinist, fara ML | M | 16 | T130 | Reguli din taxonomie + semnal "X lei pana la transport gratuit".
NX-31 | E27 | Export CRM: webhook + CSV zilnic | P2 | P2 | Lead-urile calificate ajung in sistemul clientului | M | 12 | T120 | Acelasi mecanism HMAC ca NX-52.
NX-06 | E23 | CTWA referral -> atribuire ads | P2 | P2 | Atribuire ad-spend + fereastra gratuita 72h | S | 6 | T062 | Cerere probabila de la clientii care ruleaza Click-to-WhatsApp ads.
NX-09 | E23 | Retry failed re-engagement pe template | P2 | P2 | Mai putine notificari proactive pierdute | S | 4 | T099 | Max 1 retry, doar pe joburi proactive.
NX-20 | E26 | Widget gateway SSE | P0(V2) | P2 W1 | Fundatia canalului web | L | 20 | T157 | SSE, nu WebSocket: trece prin orice proxy, reconectare nativa.
NX-21 | E26 | widget.js embeddabil (shadow DOM) | P0(V2) | P2 W2 | Embed 1 linie pe site-ul clientului | L | 24 | NX-20 | Tema per tenant + i18n + disclosure AI vizibil.
NX-22 | E26 | Canal web in gates/sender | P0(V2) | P2 W3 | Pipeline-ul existent serveste si web | M | 12 | NX-20 | Fara 24h window, debounce scurt, typing=SSE.
NX-25 | E26 | CORS/CSP + allowlist embed per tenant | P0(V2) | P2 W3 | Doar site-urile clientului pot incarca widgetul | S | 8 | NX-20 | Token public + allowlist de domenii.
NX-23 | E26 | Identitate vizitator + merge auditat | P0(V2) | P2 W4 | Acelasi client pe web si WhatsApp = un singur profil | M | 16 | NX-22 | Merge logat in audit; reversibil.
NX-24 | E26 | Context pagina in payload | P1(V2) | P2 W5 | Raspunsuri despre produsul de pe pagina curenta | S | 8 | NX-22 | page_url/product_id ca hint de retrieval.
NX-26 | E26 | Golden web + load test SSE | P1(V2) | P2 W6 | Calitate egala pe ambele canale | M | 12 | NX-22 | 200 sesiuni / 10 min, p95 sub tinta.